## Master-Defect List
Page Name | Description | Severity | Defect Type | Category | Defect Raised Date | QA Status | Devlopment Status | Developer Name | Remark
Menu Panel | Icon should be there for Dashboard | Minor | Design | Suggestion | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Email id not displayed clearly visible | Minor | Design | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Proper space should be there in action icons. | Minor | Design | Suggestion | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Column heading should be 'Official Email Id' instead of 'Office email id ' | Minor | Design | Suggestion | 2023-06-15 | Re-open | Resolved | Shraddha
Employee Master | Unnecessary space is present at the end of the grid. | Minor | Design | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Proper space should be present between column header and search field. | Minor | Design | Defect | 2023-06-15 | Re-open | Resolved | Shraddha
Employee Master | Text should be 'Inactive' instead of InActive. | Minor | Design | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Validation message should be 'Employee added successfully'. | Minor | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Validation should be there for Birth Date,should not allow future date and 18 years validation should be there. | Major | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Validation message should be as 'Enter Employee Name' | Minor | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Label text should be as 'Contact No.' | Minor | Design | Suggestion | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Employee is getting added with invalid email id. | Minor | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | S letter should be capital in Submit button text in all pages. | Minor | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Mobile number is accepting characters. | Major | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Window title should be 'Add Employee' | Minor | Design | Suggestion | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Space should be there in Email Id label it should be Email Id instead of 'EmailId'. | Minor | Design | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Color should be there for Cancel button. | Minor | Design | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Employee should not allow to delete once user is created in user master. | Major | Functional | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Submit button should not allow to click multiple times. | Major | Functional | Defect | 2023-06-15 | Closed | Resolved | Shraddha
User Master | Username should be unique. | Major | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
All Pages | Submit button should not allow to click multiple times. | Major | Functional | Defect | 2023-06-15 | Closed | Resolved | Shraddha
All Pages | Tooltip name should be same as Button text. | Minor | Design | Defect | 2023-06-15 | Open | WIP | Shraddha
All pages | The child window should not allow to close if click on on outside of child window. | Major | Functional | Defect | 2023-06-15 | Open | WIP | Shraddha
User Master | Created By,Created Date,Updated By,Updated date columns are missing. | Major | Functional | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Homepage | Page is Error message is getting displayed when click on logo. | Major | Functional | Defect | 2023-06-15 | Closed | Resolved | Shraddha
All Pages | Browser tab name and application name should be same. | Minor | Design | Defect | 2023-06-15 | Re-open | WIP | Shraddha
Parameter Master | Validation message should be proper. | Minor | Validation | Defect | 2023-06-15 | Re-open | Resolved | Shraddha
Parameter Master | Special characters and characters allowed in code field when do copy paste | Major | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Parameter Master | Space should be allowed in Parameter name. | Minor | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Parameter Master | Duplicate record is getting added when edit existing record. | Major | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Parameter Master | Window name should be as 'Add New Parameter' | Minor | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Parameter Master | Name field should allows 50 charactes only but now it is accepting more than 50. | Major | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Parameter Master | Label text should be as 'Parameter Name'. | Minor | Design | Defect | 2023-06-15 | Re-open | Resolved | Shraddha
Parameter Value Master | Parameter Group is getting reset after data is getting displayed in grid. | Major | Functional | Defect | 2023-06-15 | Open | WIP | Shraddha
Parameter Value Master | Parameter group should auto fetched and non editable when click on add new button. | Major | Functional | Defect | 2023-06-15 | Open | WIP | Shraddha
Parameter Value Master | Validation message should be as' Parameter value added successfully. | Minor | Validation | Defect | 2023-06-15 | Re-open | Resolved | Shraddha
Parameter Value Master | Parameter value field should accept 50 characters only. | Major | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Parameter Value Master | Window name should be as 'Add New Parameter Value' | Minor | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Parameter Value Master | Validation message should be proper 'Are you sure want to delete this record ?' | Minor | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Parameter Value Master | Validation message should be proper 'Parameter value deleted successfully' | Minor | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Parameter Value Master | Message should be proper if data not available on grid. | Minor | Validation | Defect | 2023-06-15 | Open | WIP | Shraddha
Speciality Master | Icon for upload speciality should be proper. | Minor | Design | Defect | 2023-06-15 | Open | WIP | Shraddha
Speciality Master | Speciality Name field should accept 50 values. | Minor | Design | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Speciality Master | Proper space should be there in upload icon and Speciality icon. | Minor | Design | Defect | 2023-06-15 | Open | WIP | Shraddha
Speciality Master | Validation message should be proper 'Specilaity added successfully'. | Minor | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Speciality Master | The speciality image upload field should accept image file only.if upload other than image then record is not displayed on grid. | Major | Functional | Defect | 2023-06-15 | Open | WIP | Shraddha
Speciality Master | Delete icon is missing | Major | Functional | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Speciality Master | Window name should be as 'Add New Speciaility' | Minor | Design | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Speciality Master | Inactive record is not getting displayed in grid. | Major | Functional | Defect | 2023-06-15 | Closed | Resolved | Shraddha
City Master | Validation message should be in sequence | Minor | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
City Master | Window name should be 'Add New City' | Minor | Design | Defect | 2023-06-15 | Closed | Resolved | Shraddha
City Master | Validaion message should be as 'City added successfully' | Minor | Validation | Defect | 2023-06-15 | Closed | Resolved | Shraddha
City Master | Inactive record is not getting displayed in grid. | Major | Functional | Defect | 2023-06-15 | Closed | Resolved | Shraddha
Employee Master | Unable to edit and update employee details. | Major | Functional | Defect | 2023-06-16 | New | WIP | Shraddha
Employee Master | Data is getting clear when vaidation message is getting displayed. It should not get clear. | Major | Functional | Defect | 2023-06-16 | New | WIP | Shraddha
User Master | Newly added Employee is not getting displayed in Employee Master. | Block | Functional | Defect | 2023-06-16 | New | WIP | Shraddha
Parameter Master | Newly added Parameter is not getting displayed in grid. | Block | Functional | Defect | 2023-06-16 | New | WIP | Shraddha
Parameter Master | Add NewParameter window should get close when new value is added. | Major | Functional | Defect | 2023-06-16 | New | WIP | Shraddha
Speciality Master | Speciality image s getting removed when updating record and set as inactive | Major | Functional | Defect | 2023-06-16 | New | WIP | Shraddha
Clinic Master | Search functionality to be removed from page. | Minor | Functional | Suggestion | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | When click on Add clinic button then improper 'Clinic Details' button is getting displayed. | Major | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | In validation message 'Insert' word should be replaced with 'Enter' | Minor | Validation | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Validation should be there for Contact No.field length. It should accept 15 numbers only. | Minor | Validation | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Working Days field should be multiselection. | Major | Functional | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Validation message should be proper. | Minor | Validation | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Working hours should contain From hours and To hours. | Major | Functional | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Contact Person field should accept 50 characters only. | Major | Validation | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Submit button text should be as 'Submit' instead of 'submit' | Minor | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Column header should be there for Block/Unblock. | Major | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Improper button is getting displayed when edit clinic details. | Major | Functional | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Improper section needs to be removed. | Major | Functional | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Text should be 'Unblock'. | Minor | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Text should be proper in message if search invalid record and the same is not present in grid. | Minor | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | All working days selected but only one day is displayed in grid. | Major | Functional | Defect | 2023-06-16 | Not Required | Not a Defect | Shraddha
Clinic Master | Working hours limit should be 24 hours | Major | Validation | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | User should allows to edit same record and page should not get refreshed after record already exists message is displayed. | Major | Functional | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Clinic Registration number field should be there and it should accept unique values. | Major | Functional | Suggestion | 2023-06-16 | Open | WIP | Shraddha
Clinic Master | Duplicate clinic details are getting saved. | Major | Functional | Suggestion | 2023-06-16 | Open | WIP | Shraddha
Clinic Master | New field needs to be added as 'Reception Contact' with two textfield. One is mandatory and another is non mandatory. | Major | Functional | Suggestion | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Helpline no and contact no. option should have checkbox with label text ' Same as Reception Contact no.' | Major | Functional | Suggestion | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Text should be as 'Inactive'. | Minor | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Add New Doctor | Validation message should be as ' Please enter only characters' | Minor | Validation | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Add New Doctor | Birth date should not allow to select as future date. | Major | Validation | Defect | 2023-06-16 | Re-open | Resolved | Shraddha
Add New Doctor | 18 years validation should be there for Date of birth. | Major | Validation | Defect | 2023-06-16 | Re-open | Resolved | Shraddha
Add New Doctor | Is Active and Is Block checkbox alignment should be proper. | Minor | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Add New Doctor | Contact Details should be mandatory. | Major | Validation | Defect | 2023-06-16 | Re-open | Resolved | Shraddha | Unable to retest as data is not getting saved.
Add New Doctor | Submit button should allow to click once only. | Major | Validation | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Add New Doctor | Heading should be there 'Add New Doctor' | Major | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Add New Doctor | Duplicate doctor details should not allowed to save. | Major | Validation | Defect | 2023-06-16 | Re-open | Resolved | Shraddha
Add New Doctor | Registration should be mandatory. | Major | Validation | Defect | 2023-06-16 | Re-open | Resolved | Shraddha
Add New Doctor | Date Picker is not working when try to add multiple details. | Major | Functional | Defect | 2023-06-16 | Open | WIP | Shraddha
Add New Doctor | After saving Pricing,Services and Specialization,Education,Experiece,Awards,Registrations the details were not getting saved. | Major | Functional | Defect | 2023-06-16 | Open | WIP | Shraddha
Add New Doctor | Username is not getting generated. | Major | Functional | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Add New Doctor | Salutation drop down field should be there with values 'Miss.',Mrs.','Mr.' | Major | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
View Doctor | Space should be there between Emailid word | Minor | Design | Defect | 2023-06-16 | Re-open | Resolved | Shraddha
View Doctor | Page name should be View Doctor Profile. | Major | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
View Doctor | Tool tip should be there for buttons and icons. | Minor | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
View Doctor | Spelling should be 'Experience' | Minor | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
View Doctor | Unable to select multiple Services and Speciality | Major | Functional | Defect | 2023-06-16 | Open | WIP | Shraddha
View Doctor | Search functionality needs to be removed. | Major | Functional | Defect | 2023-06-16 | Closed | Resolved | Shraddha
View Doctor | Color should be there for 'Headings'. | Minor | Design | Defect | 2023-06-16 | Open | WIP | Shraddha
View Doctor | Color should be there for 'Cancel' button. | Minor | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
View Doctor | Validation message should be as 'Doctor Details Updated Successfully' | Minor | Design | Defect | 2023-06-16 | Re-open | Resolved | Shraddha
View Doctor | Space should be there in Delete and Edit icon. | Minor | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Space should be there in Delete and Edit icon. | Minor | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Page name should be 'Add New Clinic' | Minor | Design | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Cancel button functionality not working. | Major | Functional | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Back button should be there. | Major | Suggestion | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Add New Doctor | Cancel button functionality not working. | Major | Functional | Defect | 2023-06-16 | Closed | Resolved | Shraddha
Clinic Master | Working Hrs and Working Days columns needs to be removed from grid. | Major | Suggestion | Defect | 2023-06-16 | Closed | Resolved | Shraddha
View Doctor | Edit functionality should be there | Major | Suggestion | Defect | 2023-06-16 | Open | WIP | Shraddha
Add New Doctor | Edit functionality should be there Pricing,Services and Specialization,Education,Experiece,Awards,Registrations the details were not getting saved. | Major | Functional | Defect | 2023-06-16 | Open | WIP | Shraddha

## Clinic Module
Page Name | Description | Severity | Defect Type | Category | Defect Raised Date | QA Status | Devlopment Status | Developer Name | Remark
Add Medical Test | Add button (+) should be there instead of "Add New" | Major | Functional | Defect | 29-06-2023 | New | WIP | Shraddha
Add Medical Test | Window name should be "Add New Medical Test" | Minor | Design | Suggestion | 30-06-2023 | New | WIP | Runali
Add Medical Test | Unnecessary space is there before and after end of the grid. | Minor | Design | Defect | 30-06-2023 | New | WIP | Runali
Add Medical Test | Test code field should be there and it should accept unique values. | Major | Functional | Suggestion | 30-06-2023 | New | WIP | Shraddha
Add Medical Test | Duplicate test records are getting added. | Major | Validation | Defect | 30-06-2023 | New | WIP | Shraddha
Add Medical Test | Rate field should allow 15 numbers. | Minor | Validation | Suggestion | 30-6-2023 | New | WIP | Shraddha
Add Medical Test | Label name should be instructions instead of instruction. | Minor | Design | Suggestion | 30-06-2023 | New | WIP | Shraddha
Add Medical Test | Place holder should be there for all felds. | Minor | Design | Suggestion | 30-06-2023 | New | WIP | Shraddha
Add New Doctor | The page title should be 'Add New Doctor' | Minor | Design | Suggestion | 30-06-2023 | New | WIP | Shraddha
Add New Doctor | Search Filter is moving while scrolling the page. | Minor | Design | Suggestion | 30-06-2023 | New | WIP | Shraddha
Add New Doctor | Back button should be display only icon istead of text. | Minor | Design | Suggestion | 30-06-2023 | New | WIP | Shraddha
Add New Doctor | Add New Doctor page should be same as Add New Doctor page displayed when login as admin. | Major | Functional | Defect | 30-06-2023 | New | WIP | Shraddha
Add New Doctor | Vertical and Horizontal scrollbar should be there to | Major | Design | Defect | 30-06-2023 | New | WIP | Shraddha
Add New Doctor | Schedule functionality not working. | Major | Functional | Defect | 30-06-2023 | New | WIP | Shraddha
Add New Doctor | Title should be "Add Time Slot" | Major | Functional | Defect | 30-06-2023 | New | WIP | Shraddha
Add New Doctor | The window should get closed when when click on submit button. | Major | Functional | Defect | 30-06-2023 | New | WIP | Shraddha
Add Time Slot | Cancel button should be there. | Major | Functional | Suggestion | 30-06-2023 | New | WIP | Shraddha
Add Time Slot | Back button should be there | Major | Functional | Defect | 30-06-2023 | New | WIP | Shraddha
Add Time Slot | Message should be 'Time slot added successfully' | Minor | Validation | Defect | 30-06-2023 | New | WIP | Shraddha
Add Time Slot | Duplicate time shlot should not allow to add. | Major | Functional | Defect | 30-06-2023 | New | WIP | Shraddha
Appointments | Design should be same as per Admin module. | Major | Design | Defect | 30-06-2023 | New | WIP | Shraddha
Appointments | Dropdown options should be in alphabetical order. | Minor | Design | Defect | 30-06-2023 | New | WIP | Shraddha
Assistant Master | Submit button text should be as Submit instead of submit | Minor | Design | Defect | 30-06-2023 | New | WIP | Shraddha
Assistant Master | Assistant is getting saved without validaton message. | Minor | Validation | Defect | 30-06-2023 | New | WIP | Shraddha
Assistant Master | Contact no. is getting saved without any validation. | Major | Validation | Defect | 30-06-2023 | New | WIP | Shraddha
Expense Management | Add and Export Button Size not proper | Minor | Design | Defect | 30-06-2023 | New | WIP | Shraddha
Expense Management | Validation message should be there if data not present in grid and click on export button. | Minor | Validation | Defect | 2023-01-07 | New | WIP | Shraddha
Expense Management | Add Expense button is not working. | Block | Functional | Defect | 2023-01-07 | New | WIP | Shraddha
Expense Management | Tooltip is missing for Export button. | Minor | Design | Defect | 2023-01-07 | New | WIP | Shraddha
Expense Management | GST column header should be as "GST". | Major | Design | Defect | 2023-01-07 | New | WIP | Shraddha
Expense Management | Column header should be Goods/Service. | Minor | Design | Defect | 2023-01-07 | New | WIP | Shraddha
Expense Management | Space should be there in GrandTota coumn header. | Minor | Design | Defect | 2023-01-07 | New | WIP | Shraddha
Expense Management | Column header should be Quantity instead of Qty. | Minor | Design | Defect | 2023-01-07 | New | WIP | Shraddha
Dispensary Management | submit button text should be Submit. | Minor | Design | Defect | 2023-01-07 | New | WIP | Shraddha
Dispensary Management | Validations should be in sequence. | Minor | Validation | Defect | 2023-01-07 | New | WIP | Shraddha
Dispensary Management | Balanced Quantity should be displayed 0 by default f user is ging to add new record. | Major | Functional | Defect | 2023-01-07 | New | WIP | Shraddha
Dispensary Management | Validation message should be as " Record added successfully" after saving new record. | Minor | Validation | Defect | 2023-02-07 | New | WIP | Shraddha
Dispensary Management | Data in grid is not getting refreshed after adding new record. | Major | Functional | Defect | 2023-02-07 | New | WIP | Shraddha
Dispensary Management | Without selecting any date if click on submit button then improper validation message id displayed. "Received date should be in between MFG date and Expiry Date!" | Major | Validation | Defect | 2023-02-07 | New | WIP | Shraddha
Dispensary Management | Sepelling should be as " Expiry" instead of " expiery" in validation message if expiry date field will be blank. | Minor | Validation | Defect | 2023-02-07 | New | WIP | Shraddha